## Slide 1: Software Engineering COMP 201
Lecturer: Sebastian Coope
Ashton Building, Room G.18
E-mail: coopes@liverpool.ac.uk
COMP 201 web-page:
http://www.csc.liv.ac.uk/~coopes/comp201
Project Management

## Slide 2: Project Management
Organising, planning and scheduling software projects

## Slide 3: Objectives
To introduce software project management and to describe its distinctive characteristics
To discuss project planning and the planning process
To show how graphical schedule representations are used by project management
To discuss the notion of risks and the risk management process

## Slide 4: Topics Covered
Management activities
Project planning
Project scheduling
Risk management

## Slide 5: Software Project Management
Concerned with activities involved in ensuring that software is delivered on time and on schedule and in accordance with the requirements of the organisations developing and procuring the software
Project management is needed because software development is always subject to budget and schedule constraints that are set by the organisation developing the software

## Slide 6: Software Management Distinctions
The product is intangible
    (cannot be seen or touched)
Software engineering is not recognized as an engineering discipline with the same status as mechanical, electrical engineering, etc.
The software development process is not standardised
Many software projects are 'one-off' projects

## Slide 7: Management Activities
Proposal writing
Project planning and scheduling
Project costing
Project monitoring and reviews
Personnel selection and evaluation
Report writing and presentations

## Slide 8: Management Commonalities
These activities are not peculiar to software management
Many techniques of engineering project management are equally applicable to software project management
Technically complex engineering systems tend to suffer from the same problems as software systems

## Slide 9: Project Staffing
May not be possible to appoint the ideal people to work on a project
  Project budget may not allow for the use of highly-paid staff
  Staff with the appropriate experience may not be available
  An organisation may wish to develop employee skills on a software project
Managers have to work within these constraints especially when (as is currently the case) there is an international shortage of skilled IT staff

## Slide 10: Project Planning
Probably the most time-consuming project management activity
Continuous activity from initial concept through to system delivery. Plans must be regularly revised as new information becomes available
Various different types of plan may be developed to support the main software project plan that is concerned with schedule and budget

## Slide 11: Types of Project Plan

## Slide 12: Project Plan Structure
Introduction
Project organisation
Risk analysis
Hardware and software resource requirements
Work breakdown
Project schedule
Monitoring and reporting mechanisms

## Slide 13: Activity Organization
Activities in a project should be organised to produce tangible outputs for management to judge progress
Milestones are the end-point of a process activity
Deliverables are project results delivered to customers
The waterfall process allows for the straightforward definition of progress milestones

## Slide 14: Milestones in the RE Process

## Slide 15: Project Scheduling
Split project into tasks and estimate time and resources required to complete each task
Organize tasks concurrently to make optimal use of workforce
Minimize task dependencies to avoid delays caused by one task waiting for another to complete
Dependent on project managers intuition and experience

## Slide 16: Scheduling Problems
Estimating the difficulty of problems and hence the cost of developing a solution is hard
Productivity is not proportional to the number of people working on a task
Adding people to a late project can make it even later because of communication overheads
The unexpected always happens. Always allow for contingency in planning

## Slide 17: Bar Charts and Activity Networks
Graphical notations used to illustrate the project schedule
Show project breakdown into tasks. Tasks should not be too small. They should take about a week or two
Activity charts show task dependencies and the critical path
Bar charts show schedule against calendar time

## Slide 18: Task Durations and Dependencies
Task | Duration (days) | Dependencies
T1 | 8 | 
T2 | 15 | 
T3 | 15 | T1(M1)
T4 | 10 | 
T5 | 10 | T2,T4 (M2)
T6 | 5 | T1,T2 (M3)
T7 | 20 | T1 (M1)
T8 | 25 | T4 (M5)
T9 | 15 | T3,T6 (M4)
T10 | 15 | T5,T7 (M7)
T11 | 7 | T9(M6)
T12 | 10 | T11(M8)

## Slide 19: Activity Network
Minimal Time to finish -> Length of longest (critical) path -> 55 days

## Slide 20: Activity Timeline

## Slide 21: Staff Allocation

## Slide 22: Risk Management
Risk management is concerned with identifying risks and drawing up plans to minimise their effect on a project.
A risk is a probability that some adverse circumstance will occur.
  Project risks affect schedule or resources
  Product risks affect the quality or performance of the software being developed
  Business risks affect the organisation developing or procuring the software

## Slide 23: Pert charts
Define
  Dependencies
  Early start
    Earliest time the task can start (given its dependencies)
  Early end
    Earliest time the task can end (given its dependencies)
  Late start
    Latest time the task can start without delaying the deadline
  Late end
    Latest time the project can end without delaying the deadline
  Slack
    Amount task can be delayed without delaying the project
    Slack = 0 task is CRITICAL

## Slide 24: Pert charts
Early
Late
Start
End
6
22
14
30
Duration 16
Task 2
Early
Late
Start
End
22
32
30
40
Duration 10
Task 3
40
Early
Late
Start
End
0
6
8
14
Duration 6
Task 1
Slack
30-22=8
Change deadline
32
22
6
22
6
0
Slack
6-6=0
Critical path
Delay will delay project
Task 2
Early Start = task 1 end (6)
Early end = Early start +
Duration 6+16=22
Task 2
Late End = task 3 late start
Early start = Early end -
Duration 30-16 = 14

## Slide 25: The Risk Management Process
Risk identification
  Identify project, product and business risks
Risk analysis
  Assess the likelihood and consequences of these risks
Risk planning
  Draw up plans to avoid or minimise the effects of the risk
Risk monitoring
  Monitor the risks throughout the project

## Slide 26: Risk Identification
Technology risks
People risks
Organisational risks
Requirements risks
Estimation risks

## Slide 27: Risks and Risk Types

## Slide 28: Risk Analysis
Assess probability and seriousness of each risk
Probability may be very low, low, moderate, high or very high
Risk effects might be catastrophic, serious, tolerable or insignificant

## Slide 29: Risk Analysis

## Slide 30: Risk Planning
Consider each risk and develop a strategy to manage that risk
Avoidance strategies
  The probability that the risk will arise is reduced
Minimisation strategies
  The impact of the risk on the project or product will be reduced
Contingency plans
  If the risk arises, contingency plans are plans to deal with that risk

## Slide 31: Risk Factors

## Slide 32: Project management Tools
The best tools are online, since
  Easy to access anywhere
  Don’t require you to set up any software
Example tools
  Too many to list here.. But have a look at Zoho
  Zoho is free and very powerful
  It has task handling, Gannt charts and milestones
  Free for <10 Meg storage

## Slide 33: Lecture Key Points
Good project management is essential for project success
The intangible nature of software causes problems for management
Managers have diverse roles but their most significant activities are planning, estimating and scheduling
Planning and estimating are iterative processes which continue throughout the course of a project

## Slide 34: Lecture Key Points
A project milestone is a predictable state where some formal report of progress is presented to management.
Risks may be project risks, product risks or business risks
Risk management is concerned with identifying risks which may affect the project and planning to ensure that these risks do not develop into major threats